## Sheet1
ID |  | Task | Task Name |  |  | Duration | Start | End Date | Finish |  |  | Predecessors
Mode
| 1 |  | Sling Project Plan V.1.0 |  |  | 124 days | Wed 10/12/1 | Fri 3/31/17
| 2 |  | Infrastructure |  |  | 25 days | Wed 10/12/1 | Mon 11/14/1
| 3 |  | Infrastructure Setup in AWS |  |  | 25 days | Wed 10/12/16 | Mon 11/14/16
| 4 |  | Database Architecture & Table Design (ER inclusive) |  |  | 8 days | Sat 10/15/16 | Tue 10/25/16
| 5 |  | Database Architecture |  |  | 6 days | Sat 10/15/16 | Fri 10/21/16
| 6 |  | Table Creation + Development Environment Testing |  |  | 2 days | Mon 10/24/16 | Tue 10/25/16 |  |  |  | 5
| 7 |  | Tentative UI and UX change Management (By Client) |  |  | 10 days | Mon 10/17/16 | Fri 10/28/16
| 8 |  | Mobile Development Process |  |  | 56 days | Wed 10/26/1 | Wed 1/11/17
| 9 |  | Login and Authentication Process + API |  |  | 18 days | Wed 10/26/1 | Fri 11/18/16
| 10 |  | Splash Screen Design |  |  | 1 day | Wed 10/26/16 | Wed 10/26/16 |  |  |  | 6
| 11 |  | Facebook Api |  |  | 1 day | Wed 10/26/16 | Wed 10/26/16 |  |  |  | 6
| 12 |  | Google Api |  |  | 1 day | Thu 10/27/16 | Thu 10/27/16 |  |  |  | 11
| 13 |  | Instagram Api |  |  | 2 days | Fri 10/28/16 | Mon 10/31/16 |  |  |  | 12
| 14 |  | App registration Page |  |  | 3 days | Wed 10/26/1 | Fri 10/28/16
| 15 |  |  | Node JS API development for the App Registration page |  | 1 day | Wed 10/26/16 | Wed 10/26/16 |  |  |  | 6
| 16 |  |  | HTML5 and CSS design for App Registration page |  | 2 days | Thu 10/27/16 | Fri 10/28/16 |  |  |  | 10
| 17 |  |  | App Registration Process + WS Integration |  | 2 days | Thu 10/27/16 | Fri 10/28/16 |  |  |  | 15
| 18 |  | Login Page development |  |  | 4 days | Wed 10/26/1 | Mon 10/31/1
| 19 |  |  | Node JS API development for the below activities |  | 2 days | Wed 10/26/16 | Thu 10/27/16 |  |  |  | 6
| 20 |  |  | HTLM 5 and CSS design |  | 2 days | Wed 10/26/16 | Thu 10/27/16 |  |  |  | 6
| 21 |  |  | Forgot Password |  | 1 day | Wed 10/26/16 | Wed 10/26/16 |  |  |  | 6
| 22 |  |  | Statement of Rights |  | 1 day | Thu 10/27/16 | Thu 10/27/16 |  |  |  | 21
| 23 |  |  | Data Policy |  | 1 day | Fri 10/28/16 | Fri 10/28/16 |  |  |  | 22
| 24 |  |  | Payment Terms & Conditions |  | 1 day | Mon 10/31/16 | Mon 10/31/16 |  |  |  | 23
| 25 |  | AWS Notification for Registration and Social Network |  |  | 4 days | Thu 10/27/16 | Tue 11/1/16
| 26 |  |  | Sending Register Notification to Registered Email ID (AWS) |  | 2 days | Thu 10/27/16 | Fri 10/28/16 |  |  |  | 15
|  |  |  | Task | External Milestone | [5 empty] | Manual Summary Rollup
|  |  |  | Split | Inactive Task | [5 empty] | Manual Summary
Project: Sling_ProjectPlan_V1.0.m |  |  |  | Milestone | Inactive Milestone | [5 empty] | Start-only
Date: Sat 10/15/16 |  |  |  | Summary | Inactive Summary |  |  |  |  | Finish-only
|  |  |  | Project Summary | Manual Task |  |  |  |  | Deadline
|  |  |  | External Tasks | Duration-only |  |  |  |  | Progress
Page 1

## Sheet2
ID |  | Task | Task Name |  |  | Duration | Start |  | Finish |  |  | Predecessors
Mode
| 27 |  |  | Sending Notification as social network notification (AWS) |  | 2 days | Mon 10/31/16 | 11/1/16 |  |  |  | 26
| 28 |  |  | Notification Design |  | 2 days | Fri 10/28/16 | 10/31/16 |  |  |  | 20
| 29 |  | Storing Payment Information(Encription & confirm the security) |  |  | 6 days | Wed 11/2/16 | 11/9/16 |  |  |  | 27
+ Image Encryption API
| 30 |  | Module Integration (without Task # 29) and Publish |  |  | 2 days | Wed 11/2/16 | 11/3/16 |  |  |  | 27
| 31 |  | Quality Testing |  |  | 3 days | Fri 11/4/16 | 11/8/16 |  |  |  | 30
| 32 |  | UAT by Client |  |  | 3 days | Wed 11/9/16 | 11/11/16 |  |  |  | 31
| 33 |  | Bug Fixing and Re-Testing |  |  | 3 days | Mon 11/14/16 | 11/16/16 |  |  |  | 32
| 34 |  | Sign-off by Client - Version 0.1 |  |  | 2 days | Thu 11/17/16 | 11/18/16 |  |  |  | 33
| 35 |  | User Landing Page + API |  |  | 22 days | Fri 10/28/16 | 11/28/1
| 36 |  | Node JS API development for the Below activities |  |  | 4 days | Fri 10/28/16 | 11/2/16 |  |  |  | 19
| 37 |  | What's on your mind |  |  | 1 day | Tue 11/1/16 | 11/1/16 |  |  |  | 24
| 38 |  | Checked-In Friends |  |  | 1 day | Wed 11/2/16 | 11/2/16 |  |  |  | 37
| 39 |  | Shots |  |  | 1 day | Thu 11/3/16 | 11/3/16 |  |  |  | 38
| 40 |  | News Wire |  |  | 1 day | Fri 11/4/16 | 11/4/16 |  |  |  | 39
| 41 |  | Like Post |  |  | 1 day | Mon 11/7/16 | 11/7/16 |  |  |  | 40
| 42 |  | Comment on Post |  |  | 1 day | Tue 11/8/16 | 11/8/16 |  |  |  | 41
| 43 |  | Share Post |  |  | 1 day | Wed 11/9/16 | 11/9/16 |  |  |  | 42
| 44 |  | Html5 and CSS design for the Landing Page |  |  | 4 days | Tue 11/1/16 | 11/4/16 |  |  |  | 16
| 45 |  | Integration with Web Services |  |  | 2 days | Thu 11/10/16 | 11/11/16 |  |  |  | 43
| 46 |  | Module Integration and Publish |  |  | 2 days | Mon 11/14/16 | 11/15/16 |  |  |  | 45
| 47 |  | Quality Testing |  |  | 3 days | Wed 11/16/16 | 11/18/16 |  |  |  | 46
| 48 |  | UAT by Client |  |  | 3 days | Mon 11/21/16 | 11/23/16 |  |  |  | 47
| 49 |  | Bug Fixing and Re-Testing |  |  | 2 days | Thu 11/24/16 | 11/25/16 |  |  |  | 48
| 50 |  | Sign-off by Client - Version 0.2 |  |  | 1 day | Mon 11/28/16 | 11/28/16 |  |  |  | 49
|  |  |  | Task | External Milestone | [5 empty] | Manual Summary Rollup
|  |  |  | Split | Inactive Task | [5 empty] | Manual Summary
Project: Sling_ProjectPlan_V1.0.m |  |  |  | Milestone | Inactive Milestone | [5 empty] | Start-only
Date: Sat 10/15/16 |  |  |  | Summary | Inactive Summary |  |  |  |  | Finish-only
|  |  |  | Project Summary | Manual Task |  |  |  |  | Deadline
|  |  |  | External Tasks | Duration-only |  |  |  |  | Progress
Page 2

## Sheet3
ID |  | Task | Task Name |  |  |  |  | Duration | Start | Finish |  |  | Predecessors
Mode
| 51 |  | Check-In + API |  |  |  |  | 9 days | Tue 11/1/16 | Fri 11/11/16
| 52 |  | Node JS API development for the Below activities |  |  |  |  | 7 days | Thu 11/3/16 | Fri 11/11/16 |  |  | 36
| 53 |  | List Restaurants based on the GPS location |  |  |  |  | 1 day | Tue 11/1/16 | Tue 11/1/16 |  |  | 13
| 54 |  | Restaurants List - Map View |  |  |  |  | 1 day | Wed 11/2/16 | Wed 11/2/16 |  |  | 53
| 55 |  | Restaurants List - List View |  |  |  |  | 1 day | Thu 11/3/16 | Thu 11/3/16 |  |  | 54
| 56 |  | Search Restaurants |  |  |  |  | 1 day | Fri 11/4/16 | Fri 11/4/16 |  |  | 55
| 57 |  | Share Post - Only Me |  |  |  |  | 1 day | Tue 11/1/16 | Tue 11/1/16 |  |  | 24
| 58 |  | Share Post - Sling Friends |  |  |  |  | 1 day | Wed 11/2/16 | Wed 11/2/16 |  |  | 57
| 59 |  | Share Post - Public |  |  |  |  | 1 day | Thu 11/3/16 | Thu 11/3/16 |  |  | 58
| 60 |  | HTML5 and CSS design for the Check-In pages |  |  |  |  | 3 days | Wed 11/2/16 | Fri 11/4/16 |  |  | 20
| 61 |  | Integration with Web Services |  |  |  |  | 1 day | Fri 11/4/16 | Fri 11/4/16 |  |  | 59
| 62 |  | Restaurant Landing Page & Sling + API |  |  |  |  | 13 days | Mon 11/7/16 | Wed 11/23/1
| 63 |  | Node JS API development for the Below activities |  |  |  |  | 2 days | Thu 11/10/16 | Fri 11/11/16 |  |  | 29
| 64 |  | HTML5 and CSS design for the Rest. Landing Page |  |  |  |  | 3 days | Mon 11/7/16 | Wed 11/9/16 |  |  | 44
| 65 |  | Share Restaurant |  |  |  |  | 2 days | Mon 11/7/16 | Tue 11/8/16 |  |  | 56
| 66 |  | Like Restaurant |  |  |  |  | 2 days | Wed 11/9/16 | Thu 11/10/16 |  |  | 65
| 67 |  | Comment Restaurant |  |  |  |  | 2 days | Fri 11/11/16 | Mon 11/14/16 |  |  | 66
| 68 |  | Menu Listing |  |  |  |  | 2 days | Mon 11/7/16 | Tue 11/8/16 |  |  | 61
| 69 |  | Search Menu |  |  |  |  | 2 days | Wed 11/9/16 | Thu 11/10/16 |  |  | 68
| 70 |  | Cart Management |  |  |  |  | 3 days | Mon 11/14/16 | Wed 11/16/16 |  |  | 45
| 71 |  | Credit Card Save Option |  |  |  |  | 3 days | Thu 11/17/16 | Mon 11/21/16 |  |  | 70
| 72 |  | Terms & Conditions |  |  |  |  | 1 day | Fri 11/11/16 | Fri 11/11/16 |  |  | 69
| 73 |  | Share Gift |  |  |  |  | 2 days | Mon 11/14/16 | Tue 11/15/16 |  |  | 72
| 74 |  | Integration with Web Services |  |  |  |  | 2 days | Tue 11/22/16 | Wed 11/23/16 |  |  | 71
|  |  |  | Task |  |  | External Milestone |  |  |  |  | Manual Summary Rollup
|  |  |  | Split |  |  | Inactive Task |  |  |  |  | Manual Summary
Project: Sling_ProjectPlan_V1.0.m |  |  |  |  | Milestone |  | Inactive Milestone |  |  |  |  | Start-only
Date: Sat 10/15/16 |  |  |  | Summary |  | Inactive Summary |  |  |  |  | Finish-only
|  |  |  | Project Summary |  | Manual Task |  |  |  |  | Deadline
|  |  |  | External Tasks |  | Duration-only |  |  |  |  | Progress
Page 3

## Sheet4
ID |  | Task | Task Name |  |  |  | Duration | Start | Finish |  |  | Predecessors
Mode
| 75 |  | Payment Gatway Integration + API |  |  |  | 5 days | Mon 11/14/1 | Fri 11/18/16
| 76 |  | Payment Gateway |  |  |  | 5 days | Mon 11/14/16 | Fri 11/18/16 |  |  | 63
| 77 |  | HTML5 and CSS design for the Payment Gateway |  |  |  | 2 days | Mon 11/14/16 | Tue 11/15/16 |  |  | 63
| 78 |  | News Wire - Update Event in Db & Social + API |  |  |  | 25 days | Thu 11/10/16 | Wed 12/14/1
| 79 |  | Node JS API development for the Below activities |  |  |  | 4 days | Mon | Thu 11/17/16 |  |  | 52
11/14/16
| 80 |  | HTML5 and CSS design for the News Wire Pages |  |  |  | 2 days | Thu 11/10/16 | Fri 11/11/16 |  |  | 64
| 81 |  | Update Gift Sent |  |  |  | 1 day | Tue 11/15/16 | Tue 11/15/16 |  |  | 67
| 82 |  | Update Gift Received |  |  |  | 1 day | Wed 11/16/16 | Wed 11/16/16 |  |  | 81
| 83 |  | Update Birthday Reminder |  |  |  | 1 day | Wed 11/16/16 | Wed 11/16/16 |  |  | 73
| 84 |  | Update Photo |  |  |  | 1 day | Thu 11/17/16 | Thu 11/17/16 |  |  | 83
| 85 |  | Integration with Web Services |  |  |  | 2 days | Fri 11/18/16 | Mon 11/21/16 |  |  | 84
| 86 |  | Module Integration and Publish for CheckIn, Rest. |  |  |  | 2 days | Tue 11/22/16 | Wed |  |  | 85
|  |  | Landing, Payment Gateway and News Wire | [5 empty] | 11/23/16
| 87 |  | Quality Testing |  |  |  | 5 days | Thu 11/24/16 | Wed 11/30/16 |  |  | 86
| 88 |  | UAT by Client |  |  |  | 4 days | Thu 12/1/16 | Tue 12/6/16 |  |  | 87
| 89 |  | Bug Fixing and Re-Testing |  |  |  | 4 days | Wed 12/7/16 | Mon 12/12/16 |  |  | 88
| 90 |  | Sign-off by Client - Version 0.3 |  |  |  | 2 days | Tue 12/13/16 | Wed 12/14/16 |  |  | 89
| 91 |  | Friends + API |  |  |  | 6 days | Thu 11/17/16 | Thu 11/24/16
| 92 |  | Node JS API development for the Below activities |  |  |  | 2 days | Fri 11/18/16 | Mon |  |  | 79
11/21/16
| 93 |  | HTML5 and CSS design for the Friends Page |  |  |  | 2 days | Tue 11/22/16 | Wed 11/23/16 |  |  | 92
| 94 |  | Add Filter For :- All ¦ Checked In ¦ Friends ¦ Others |  |  |  | 1 day | Thu 11/17/16 | Thu 11/17/16 |  |  | 82
| 95 |  | List All Friends |  |  |  | 1 day | Fri 11/18/16 | Fri 11/18/16 |  |  | 94
| 96 |  | Search Friends |  |  |  | 1 day | Mon 11/21/16 | Mon 11/21/16 |  |  | 95
| 97 |  | Integration with Web Services |  |  |  | 3 days | Tue 11/22/16 | Thu 11/24/16 |  |  | 92
|  |  |  | Task |  | External Milestone |  |  |  |  | Manual Summary Rollup
|  |  |  | Split |  | Inactive Task |  |  |  |  | Manual Summary
Project: Sling_ProjectPlan_V1.0.m |  |  |  |  | Milestone | Inactive Milestone |  |  |  |  | Start-only
Date: Sat 10/15/16 |  |  |  | Summary |  | Inactive Summary |  |  |  | Finish-only
|  |  |  | Project Summary |  | Manual Task |  |  |  | Deadline
|  |  |  | External Tasks |  | Duration-only |  |  |  | Progress
Page 4

## Sheet5
ID | Task | Task Name |  |  |  | Duration | Start |  | Finish |  |  | Predecessors
Mode
98 |  | Venue Management + API |  |  |  | 3 days | Mon 11/21/1 |  | Wed 11/23/1
99 |  | Node JS API development for the Below activities |  |  |  | 1 day | Mon 11/21/16 | Mon 11/21/16 |  |  |  | 76
100 |  | HTML5 and CSS design for the Venue Mgmt Page |  |  |  | 1 day | Tue 11/22/16 | Tue 11/22/16 |  |  |  | 99
101 |  | List Restaurants based on the current GPS location |  |  |  | 1 day | Tue 11/22/16 | Tue 11/22/16 |  |  |  | 85
102 |  | Integration with Web Services |  |  |  | 1 day | Wed 11/23/16 |  | Wed 11/23/16 |  |  | 101
103 |  | My Sling + API |  |  |  | 27 days | Tue 11/22/16 |  | Wed 12/28/1
104 |  | Node JS API development for the Below activities |  |  |  | 3 days | Tue 11/22/16 | Thu 11/24/16 |  |  |  | 99
105 |  | HTML5 and CSS design for the My Sling Page |  |  |  | 2 days | Thu 11/24/16 |  | Fri 11/25/16 |  |  | 187
106 |  | List all Sling Items |  |  |  | 1 day | Mon 11/28/16 |  | Mon 11/28/16 |  |  | 49
107 |  | Received Sling Items |  |  |  | 1 day | Tue 11/29/16 |  | Tue 11/29/16 |  |  | 106
108 |  | Sent Sling Items |  |  |  | 1 day | Wed 11/30/16 |  | Wed 11/30/16 |  |  | 107
109 |  | Invoiced Sling Items |  |  |  | 1 day | Thu 12/1/16 |  | Thu 12/1/16 |  |  | 108
110 |  | Expired Sling Items |  |  |  | 1 day | Fri 12/2/16 |  | Fri 12/2/16 |  |  | 109
111 |  | Integration with Web Services |  |  |  | 1 day | Mon 12/5/16 |  | Mon 12/5/16 |  |  | 110
112 |  | Module Integration and Publish for Friends, Venue and |  |  |  | 2 days | Tue 12/6/16 | Wed 12/7/16 |  |  |  | 111
My Sling
113 |  | Quality Testing |  |  |  | 7 days | Thu 12/8/16 |  | Fri 12/16/16 |  |  | 112
114 |  | UAT by Client |  |  |  | 4 days | Mon 12/19/16 |  | Thu 12/22/16 |  |  | 113
115 |  | Bug Fixing and Re-Testing |  |  |  | 3 days | Fri 12/23/16 |  | Tue 12/27/16 |  |  | 114
116 |  | Sign-off by Client - Version 0.4 |  |  |  | 1 day | Wed 12/28/16 |  | Wed 12/28/16 |  |  | 115
117 |  | Settings + API |  |  |  | 6 days | Tue 11/22/16 |  | Tue 11/29/16
118 |  | Node JS API development for the Below activities |  |  |  | 1 day | Tue 11/22/16 | Tue 11/22/16 |  |  |  | 92
119 |  | HTML5 and CSS design for the Settings Page |  |  |  | 1 day | Mon 11/28/16 |  | Mon 11/28/16 |  |  | 192
120 |  | Notification Settings[Only Me, Only Sling Users, Only Friends & |  |  |  | 2 days | Fri 11/25/16 | Mon 11/28/16 |  |  |  | 97
|  |  | Task |  | External Milestone | [5 empty] | Manual Summary Rollup
|  |  | Split |  | Inactive Task | [5 empty] | Manual Summary
Project: Sling_ProjectPlan_V1.0.m |  |  |  | Milestone | Inactive Milestone | [5 empty] | Start-only
Date: Sat 10/15/16 |  |  | Summary |  | Inactive Summary |  |  |  |  | Finish-only
|  |  | Project Summary |  | Manual Task |  |  |  |  | Deadline
|  |  | External Tasks |  | Duration-only |  |  |  |  | Progress
Page 5

## Sheet6
ID | Task | Task Name |  |  |  | Duration | Start | Finish |  |  | Predecessors
Mode
121 |  | Sound in the App |  |  |  | 1 day | Thu 11/24/16 | Thu 11/24/16 |  |  | 102
122 |  | Integration with Web Services |  |  |  | 1 day | Tue 11/29/16 | Tue 11/29/16 |  |  | 119
123 |  | Shots + API |  |  |  | 8 days | Fri 11/25/16 | Tue 12/6/16
124 |  | Node JS API development for the Below activities |  |  |  | 3 days | Fri 11/25/16 | Tue 11/29/16 |  |  | 104
125 |  | HTML5 and CSS design for the Shots Page |  |  |  | 2 days | Mon 11/28/16 | Tue 11/29/16 |  |  | 105
126 |  | List All My Shots |  |  |  | 2 days | Wed 11/30/16 | Thu 12/1/16 |  |  | 124
127 |  | List All My Friends Shots |  |  |  | 1 day | Fri 12/2/16 | Fri 12/2/16 |  |  | 126
128 |  | Search Photo |  |  |  | 1 day | Mon 12/5/16 | Mon 12/5/16 |  |  | 127
129 |  | Integration with Web Services |  |  |  | 1 day | Tue 12/6/16 | Tue 12/6/16 |  |  | 128
130 |  | Notification + API (AWS) |  |  |  | 9 days | Wed 11/23/1 | Mon 12/5/16
131 |  | Node JS API development for the Below activities |  |  |  | 6 days | Wed | Wed |  |  | 118
[7 empty] | 11/23/16 | 11/30/16
132 |  | HTML5 and CSS design for the Notificaitons |  |  |  | 3 days | Wed 11/30/16 | Fri 12/2/16 |  |  | 125
133 |  | List All Notifications |  |  |  | 1 day | Fri 11/25/16 | Fri 11/25/16 |  |  | 121
134 |  | Gave Notifications |  |  |  | 1 day | Mon 11/28/16 | Mon 11/28/16 |  |  | 133
135 |  | Received Notifications |  |  |  | 1 day | Tue 11/29/16 | Tue 11/29/16 |  |  | 134
136 |  | Send Facebook Notification |  |  |  | 1 day | Wed 11/30/16 | Wed 11/30/16 |  |  | 135
137 |  | Send Email |  |  |  | 1 day | Thu 12/1/16 | Thu 12/1/16 |  |  | 136
138 |  | App Notification |  |  |  | 1 day | Fri 12/2/16 | Fri 12/2/16 |  |  | 137
139 |  | Integration with Web Services |  |  |  | 1 day | Mon 12/5/16 | Mon 12/5/16 |  |  | 138
140 |  | My Profile + API |  |  |  | 8 days | Tue 11/29/16 | Thu 12/8/16
141 |  | Node JS API development for the Below activities |  |  |  | 6 days | Thu 12/1/16 | Thu 12/8/16 |  |  | 131
142 |  | HTML5 and CSS Design for My Profile Page |  |  |  | 3 days | Tue 11/29/16 | Thu 12/1/16 |  |  | 119
143 |  | Display Personal Details |  |  |  | 1 day | Wed 11/30/16 | Wed 11/30/16 |  |  | 122
144 |  | List Visited Vinue |  |  |  | 1 day | Thu 12/1/16 | Thu 12/1/16 |  |  | 143
|  |  | Task |  | External Milestone |  |  |  |  | Manual Summary Rollup
|  |  | Split |  | Inactive Task |  |  |  |  | Manual Summary
Project: Sling_ProjectPlan_V1.0.m |  |  |  | Milestone | Inactive Milestone |  |  |  |  | Start-only
Date: Sat 10/15/16 |  |  | Summary |  | Inactive Summary |  |  |  | Finish-only
|  |  | Project Summary |  | Manual Task |  |  |  | Deadline
|  |  | External Tasks |  | Duration-only |  |  |  | Progress
Page 6

## Sheet7
ID | Task | Task Name |  |  |  | Duration | Start | Finish |  |  | Predecessors
Mode
145 |  | List Friend List |  |  |  | 1 day | Fri 12/2/16 | Fri 12/2/16 |  |  | 144
146 |  | List all the post |  |  |  | 1 day | Mon 12/5/16 | Mon 12/5/16 |  |  | 145
147 |  | Profile Edit Page & Change Password |  |  |  | 1 day | Tue 12/6/16 | Tue 12/6/16 |  |  | 146
148 |  | Integration with Web Services |  |  |  | 2 days | Wed 12/7/16 | Thu 12/8/16 |  |  | 147
149 |  | Mobile Waiter - Dashboard |  |  |  | 7 days | Tue 12/6/16 | Wed 12/14/1
150 |  | Node JS API development for the Below activities |  |  |  | 2 days | Fri 12/9/16 | Mon 12/12/16 |  |  | 141
151 |  | Today Total Sling Credit[Filer : Date] for that particular Waiter |  |  |  | 2 days | Tue 12/6/16 | Wed 12/7/16 |  |  | 146
152 |  | HTML5 and CSS Design for Waiter DashPage |  |  |  | 2 days | Thu 12/8/16 | Fri 12/9/16 |  |  | 151
153 |  | Integration with Web Services |  |  |  | 2 days | Tue 12/13/16 | Wed 12/14/16 |  |  | 150
154 |  | Mobile Waiter - Scan and Order Creation in POS |  |  |  | 7 days | Tue 12/13/16 | Wed 12/21/1
155 |  | Node JS API development for the Below activities |  |  |  | 2 days | Tue 12/13/16 | Wed 12/14/16 |  |  | 89
156 |  | Scan the QR Code & Create the order in POS thru POS API |  |  |  | 2 days | Thu 12/15/16 | Fri 12/16/16 |  |  | 155
157 |  | HTML5 and CSS Design for Scan and Order Creation |  |  |  | 2 days | Mon | Tue 12/20/16 |  |  | 156
|  | page |  |  |  |  | 12/19/16
158 |  | Integration with Web Services |  |  |  | 1 day | Wed 12/21/16 | Wed 12/21/16 |  |  | 157
159 |  | Mobile Waiter - My Profile |  |  |  | 28 days | Mon 12/5/16 | Wed 1/11/17
160 |  | Node JS API development for the Below activities |  |  |  | 4 days | Wed 12/28/16 | Mon 1/2/17 |  |  | 115
161 |  | HTML5 and CSS Design for Profile Page |  |  |  | 3 days | Mon 12/5/16 | Wed 12/7/16 |  |  | 132
162 |  | Edit Profile Details |  |  |  | 1 day | Thu 12/8/16 | Thu 12/8/16 |  |  | 151
163 |  | Change Password |  |  |  | 1 day | Fri 12/9/16 | Fri 12/9/16 |  |  | 162
164 |  | Forgot Password |  |  |  | 1 day | Mon 12/12/16 | Mon 12/12/16 |  |  | 163
165 |  | Integration with Web Services |  |  |  | 2 days | Tue 12/13/16 | Wed 12/14/16 |  |  | 164
166 |  | Module Integration and Publish for Notifications, My |  |  |  | 3 days | Thu 12/15/16 | Mon |  |  | 165
|  | Profile, Waiter Dashboard, Scan and Order and Waiter | [5 empty] | 12/19/16
Profile
167 |  | Quality Testing |  |  |  | 6 days | Tue 12/20/16 | Tue 12/27/16 |  |  | 166
|  |  | Task |  | External Milestone |  |  |  |  | Manual Summary Rollup
|  |  | Split |  | Inactive Task |  |  |  |  | Manual Summary
Project: Sling_ProjectPlan_V1.0.m |  |  |  | Milestone | Inactive Milestone |  |  |  |  | Start-only
Date: Sat 10/15/16 |  |  | Summary |  | Inactive Summary |  |  |  | Finish-only
|  |  | Project Summary |  | Manual Task |  |  |  | Deadline
|  |  | External Tasks |  | Duration-only |  |  |  | Progress
Page 7

## Sheet8
ID | Task | Task Name |  |  |  | Duration | Start |  | Finish |  |  | Predecessors
Mode
168 |  | UAT by Client |  |  |  | 4 days | Wed 12/28/16 | Mon 1/2/17 |  |  |  | 167
169 |  | Bug Fixing and Re-Testing |  |  |  | 6 days | Tue 1/3/17 | Tue 1/10/17 |  |  |  | 168
170 |  | Sign-off by Client - Version 0.5 |  |  |  | 1 day | Wed 1/11/17 | Wed 1/11/17 |  |  |  | 169
171 |  | Web Page Development Process |  |  |  | 60 days | Wed 10/19/1 | Tue 1/10/17
172 |  | Web - Entity Admin |  |  |  | 13 days | Wed 10/19/1 | Fri 11/4/16
173 |  | Web Server Installation & Node JS Installation |  |  |  | 3 days | Wed 10/19/16 | Fri 10/21/16
174 |  | Setup a Development Environment |  |  |  | 6 days | Mon 10/24/16 | Mon 10/31/16 |  |  |  | 173
175 |  | Setup an UAT Environment |  |  |  | 4 days | Tue 11/1/16 | Fri 11/4/16 |  |  |  | 174
176 |  | Web - Entity Admin Dashboard |  |  |  | 27 days | Wed 11/16/1 | Thu 12/22/16
177 |  | Currrently Checked-In Sling Users |  |  |  | 3 days | Tue 12/13/16 | Thu 12/15/16 |  |  |  | 150
178 |  | Today Total Sling Credit[Filer : Date] |  |  |  | 1 day | Fri 12/16/16 | Fri 12/16/16 |  |  |  | 177
179 |  | Today Upcoming Sling Users |  |  |  | 2 days | Mon 12/19/16 | Tue 12/20/16 |  |  |  | 178
180 |  | Check-In/Check-Out Notification |  |  |  | 2 days | Wed 12/21/16 | Thu 12/22/16 |  |  |  | 179
181 |  | HTML5 and CSS design for the Entity Admin Dashboard |  |  |  | 2 days | Wed 11/16/16 |  | Thu 11/17/16 |  |  | 77
182 |  | Web - Entity Admin - Order History |  |  |  | 30 days | Fri 11/18/16 | Thu 12/29/16
183 |  | Display Order Details with status |  |  |  | 5 days | Fri 12/23/16 | Thu 12/29/16 |  |  |  | 180
184 |  | HTML5 and CSS design for the Order History |  |  |  | 2 days | Fri 11/18/16 | Mon 11/21/16 |  |  |  | 181
185 |  | Web Entity Admin - Manage Users |  |  |  | 30 days | Wed 11/23/1 | Tue 1/3/17
186 |  | Add/Edit/View/Deactivate/Delete |  |  |  | 3 days | Fri 12/30/16 | Tue 1/3/17 |  |  |  | 183
187 |  | HTML5 and CSS design for the Manager Users |  |  |  | 1 day | Wed 11/23/16 |  | Wed 11/23/16 |  |  | 100
188 |  | Web - Entity Admin - My Profile + API |  |  |  | 34 days | Thu 11/24/16 | Tue 1/10/17
189 |  | Edit Profile Details |  |  |  | 2 days | Wed 1/4/17 | Thu 1/5/17 |  |  |  | 186
190 |  | Change Password |  |  |  | 1 day | Fri 1/6/17 | Fri 1/6/17 |  |  |  | 189
191 |  | Forgot Password |  |  |  | 2 days | Mon 1/9/17 | Tue 1/10/17 |  |  |  | 190
192 |  | HTML5 and CSS design for the My Profile |  |  |  | 2 days | Thu 11/24/16 | Fri 11/25/16 |  |  |  | 93
193 |  | Web Page for Sling Admin |  |  |  | 64 days | Mon 11/7/16 | Thu 2/2/17
|  |  | Task |  | External Milestone | [5 empty] | Manual Summary Rollup
|  |  | Split |  | Inactive Task | [5 empty] | Manual Summary
Project: Sling_ProjectPlan_V1.0.m |  |  |  | Milestone | Inactive Milestone | [5 empty] | Start-only
Date: Sat 10/15/16 |  |  | Summary |  | Inactive Summary |  |  |  |  | Finish-only
|  |  | Project Summary |  | Manual Task |  |  |  |  | Deadline
|  |  | External Tasks |  | Duration-only |  |  |  |  | Progress
Page 8

## Sheet9
ID | Task | Task Name |  |  |  | Duration | Start |  | Finish |  |  | Predecessors
Mode
194 |  | Sling Super Admin - Manage Users |  |  |  | 50 days | Mon 11/7/16 | Fri 1/13/17
195 |  | Add/Edit/View/Deactivate/Delete |  |  |  | 3 days | Wed 1/11/17 | Fri 1/13/17 |  |  |  | 169
196 |  | HTML5 and CSS Development of Manage users |  |  |  | 2 days | Mon 11/7/16 |  | Tue 11/8/16 |  |  | 60
197 |  | Sling Super Admin - Manage Post |  |  |  | 48 days | Wed 11/9/16 | Fri 1/13/17
198 |  | Deactivate/Delete any POST |  |  |  | 2 days | Wed 1/11/17 | Thu 1/12/17 |  |  |  | 191
199 |  | Deactivate/Delete any Comments |  |  |  | 1 day | Fri 1/13/17 | Fri 1/13/17 |  |  |  | 198
200 |  | HTML5 and CSS development of Manage Post |  |  |  | 2 days | Wed 11/9/16 |  | Thu 11/10/16 |  |  | 196
201 |  | Sling Super Admin - Manage Restaurants |  |  |  | 59 days | Fri 11/11/16 | Wed 2/1/17
202 |  | Add/Edit/View/Deactivate/Delete |  |  |  | 3 days | Mon 1/16/17 | Wed 1/18/17 |  |  |  | 195
203 |  | POS API Settings Page |  |  |  | 2 days | Thu 1/19/17 | Fri 1/20/17 |  |  |  | 202
204 |  | Upload Menu Items from Excel Template |  |  |  | 4 days | Mon 1/23/17 | Thu 1/26/17 |  |  |  | 203
205 |  | Manual Menu Item - API |  |  |  | 4 days | Fri 1/27/17 | Wed 2/1/17 |  |  |  | 204
206 |  | HTML5 and CSS development of Manage Restaurants |  |  |  | 2 days | Fri 11/11/16 |  | Mon 11/14/16 |  |  | 200
207 |  | Sling Super Admin - Reports |  |  |  | 11 days | Mon 1/16/17 | Mon 1/30/17
208 |  | Payment Reports |  |  |  | 3 days | Mon 1/16/17 | Wed 1/18/17 |  |  |  | 199
209 |  | Order Reports |  |  |  | 3 days | Thu 1/19/17 | Mon 1/23/17 |  |  |  | 208
210 |  | Item Reports |  |  |  | 3 days | Tue 1/24/17 | Thu 1/26/17 |  |  |  | 209
211 |  | HTML5 and CSS development of Reports |  |  |  | 2 days | Fri 1/27/17 | Mon 1/30/17 |  |  |  | 210
212 |  | Sling Super Admin - My Profile |  |  |  | 5 days | Fri 1/27/17 | Thu 2/2/17
213 |  | Edit Profile Details |  |  |  | 1 day | Fri 1/27/17 | Fri 1/27/17 |  |  |  | 210
214 |  | Change Password |  |  |  | 1 day | Mon 1/30/17 | Mon 1/30/17 |  |  |  | 213
215 |  | Forgot Password |  |  |  | 1 day | Tue 1/31/17 | Tue 1/31/17 |  |  |  | 214
216 |  | HTML5 and CSS development of My Profile page |  |  |  | 2 days | Wed 2/1/17 |  | Thu 2/2/17 |  |  | 215
217 |  | Web Page Testing Process |  |  |  | 40 days | Wed 12/28/1 | Tue 2/21/17
218 |  | Web - Entity Admn dashboard Module |  |  |  | 5 days | Wed 12/28/16 | Tue 1/3/17 |  |  |  | 167
219 |  | Web - Entity Admin - Order History Module |  |  |  | 3 days | Fri 12/30/16 | Tue 1/3/17 |  |  |  | 183
|  |  | Task |  | External Milestone | [5 empty] | Manual Summary Rollup
|  |  | Split |  | Inactive Task | [5 empty] | Manual Summary
Project: Sling_ProjectPlan_V1.0.m |  |  |  | Milestone | Inactive Milestone | [5 empty] | Start-only
Date: Sat 10/15/16 |  |  | Summary |  | Inactive Summary |  |  |  |  | Finish-only
|  |  | Project Summary |  | Manual Task |  |  |  |  | Deadline
|  |  | External Tasks |  | Duration-only |  |  |  |  | Progress
Page 9

## Sheet10
ID | Task | Task Name | Duration | Start | Finish | Predecessors
Mode
220 |  | Web - Entity Admin - Manager Users | 3 days | Wed 1/4/17 | Fri 1/6/17 | 218
221 |  | Web - Entity Admin - My Profile Module | 3 days | Wed 1/11/17 | Fri 1/13/17 | 191
222 |  | Sling Super Admin - Manager Users Module | 3 days | Mon 1/16/17 | Wed 1/18/17 | 195
223 |  | Sling Super Admin - Manage Post Module | 3 days | Mon 1/16/17 | Wed 1/18/17 | 199
224 |  | Sling Super Admin - Manage Restaurants Module | 2 days | Thu 2/2/17 | Fri 2/3/17 | 205
225 |  | Sling Super Admin - Reports | 4 days | Tue 1/31/17 | Fri 2/3/17 | 211
226 |  | Sling Super Admin - My Profile | 2 days | Fri 2/3/17 | Mon 2/6/17 | 216
227 |  | Bug Fixing on Super Admin & Entity Admin | 8 days | Tue 2/7/17 | Thu 2/16/17 | 226
228 |  | Final Testing of Web Solution | 3 days | Fri 2/17/17 | Tue 2/21/17 | 227
229 |  | User Acceptance Testing | 53 days | Wed 1/4/17 | Fri 3/17/17
230 |  | Alpha Testing and release to UAT Environment (WEB Only) | 7 days | Wed 2/22/17 | Thu 3/2/17 | 228
231 |  | Use Case Document | 20 days | Wed 1/4/17 | Tue 1/31/17 | 218
232 |  | Bug Fixing (Issues using Mantis Tracker) | 7 days | Fri 3/3/17 | Mon 3/13/17 | 230
233 |  | BETA Testing and release to UAT Environment | 3 days | Tue 3/14/17 | Thu 3/16/17 | 232
234 |  | Deployment of BETA Version | 1 day | Fri 3/17/17 | Fri 3/17/17 | 233
235 |  | Go LIVE Events | 10 days | Mon 3/20/17 | Fri 3/31/17
236 |  | Publish .APK file in Google Play | 3 days | Mon 3/20/17 | Wed 3/22/17 | 234
237 |  | Publish iOS Version in App Store | 4 days | Mon 3/20/17 | Thu 3/23/17 | 234
238 |  | Hosting the Web Solution | 2 days | Tue 3/28/17 | Wed 3/29/17 | 237
239 |  | User Manual | 10 days | Mon 3/20/17 | Fri 3/31/17 | 234
240 |  | Hand over and Training | 1 day | Thu 3/30/17 | Thu 3/30/17 | 238

## Sheet11
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 10

## Sheet12
Resource Names | 2, '16 | Oct 9, '16 | Oct 16, '16 | Oct 23, '16 | Oct 30, '16
M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S
Reddy
Anand |  |  |  | Anand
Anand |  |  |  |  | Anand
Client's Designer |  |  |  |  | Client's Designer
Selva |  |  |  |  | Selva
Guru |  |  |  |  | Guru
Guru |  |  |  |  | Guru
Guru |  |  |  |  | Guru
Prabakar |  |  |  |  | Prabakar
Selva |  |  |  |  | Selva
Vinoth |  |  |  |  | Vinoth
Elan |  |  |  |  | Elan
Reshmi |  |  |  |  | Reshmi
Shunmugam |  |  |  |  | Shunmugam
Shunmugam |  |  |  |  | Shunmugam
Shunmugam |  |  |  |  | Shunmugam
Shunmugam |  |  |  |  | Shunmugam
Prabakar |  |  |  |  | Prabakar
|  | Task | External Milestone |  | Manual Summary Rollup
|  | Split | Inactive Task |  | Manual Summary
Project: Sling_ProjectPlan_V1.0.m |  | Milestone | Inactive Milestone |  | Start-only
Date: Sat 10/15/16 |  | Summary | Inactive Summary |  | Finish-only
|  | Project Summary | Manual Task |  | Deadline
|  | External Tasks | Duration-only |  | Progress
Page 11

## Sheet13
Resource Names | 2, '16 | Oct 9, '16 | Oct 16, '16 | Oct 23, '16 | Oct 30, '16
M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S
Prabakar |  |  |  |  | Prabakar
Reshmi |  |  |  |  | Reshmi
Prabakar
Baskar |  |  |  |  | Baska
QA Team
Client
Prabakar
Client
Elan |  |  |  |  | Elan
Vinoth |  |  |  |  | Vinoth
Vinoth |  |  |  |  | Vinoth
Vinoth |  |  |  |  | Vinot
Vinoth |  |  |  |  | V
Vinoth
Vinoth
Vinoth
Selva |  |  |  |  | S
Vinoth
Baskar
QA Team
Client
Vinoth
Client
|  | Task | External Milestone |  | Manual Summary Rollup
|  | Split | Inactive Task |  | Manual Summary
Project: Sling_ProjectPlan_V1.0.m |  | Milestone | Inactive Milestone |  | Start-only
Date: Sat 10/15/16 |  | Summary | Inactive Summary |  | Finish-only
|  | Project Summary | Manual Task |  | Deadline
|  | External Tasks | Duration-only |  | Progress
Page 12

## Sheet14
Resource Names | 2, '16 | Oct 9, '16 | Oct 16, '16 | Oct 23, '16 | Oct 30, '16
M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S
Elan
Guru |  |  |  |  | Guru
Guru |  |  |  |  | Guru
Guru |  |  |  |  | Guru
Guru |  |  |  |  | G
Shunmugam |  |  |  |  | Shunmugam
Shunmugam |  |  |  |  | Shunmuga
Shunmugam |  |  |  |  | Shun
Reshmi |  |  |  |  | R
Shunmugam |  |  |  |  | S
Prabakar
Selva
Guru
Guru
Guru
Shunmugam
Shunmugam
Vinoth
Vinoth
Shunmugam
Shunmugam
Vinoth
|  | Task | External Milestone |  | Manual Summary Rollup
|  | Split | Inactive Task |  | Manual Summary
Project: Sling_ProjectPlan_V1.0.m |  | Milestone | Inactive Milestone |  | Start-only
Date: Sat 10/15/16 |  | Summary | Inactive Summary |  | Finish-only
|  | Project Summary | Manual Task |  | Deadline
|  | External Tasks | Duration-only |  | Progress
Page 13

## Sheet15
Resource Names | 2, '16 | Oct 9, '16 | Oct 16, '16 | Oct 23, '16 | Oct 30, '16
M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S
Prabakar
Selva
Elan
Selva
Guru
Guru
Shunmugam
Shunmugam
Shunmugam
Baskar
QA Team
Client
Prabakar
Client
Elan
Reshmi
Guru
Guru
Guru
Guru
|  | Task | External Milestone |  | Manual Summary Rollup
|  | Split | Inactive Task |  | Manual Summary
Project: Sling_ProjectPlan_V1.0.m |  | Milestone | Inactive Milestone |  | Start-only
Date: Sat 10/15/16 |  | Summary | Inactive Summary |  | Finish-only
|  | Project Summary | Manual Task |  | Deadline
|  | External Tasks | Duration-only |  | Progress
Page 14

## Sheet16
Resource Names | 2, '16 | Oct 9, '16 | Oct 16, '16 | Oct 23, '16 | Oct 30, '16
M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S
Prabakar
Selva
Shunmugam
Shunmugam
Prabakar
Selva
Vinoth
Vinoth
Vinoth
Vinoth
Vinoth
Vinoth
Baskar
QA Team
Client
Prabakar
Client
Elan
Reshmi
Guru
|  | Task | External Milestone |  | Manual Summary Rollup
|  | Split | Inactive Task |  | Manual Summary
Project: Sling_ProjectPlan_V1.0.m |  | Milestone | Inactive Milestone |  | Start-only
Date: Sat 10/15/16 |  | Summary | Inactive Summary |  | Finish-only
|  | Project Summary | Manual Task |  | Deadline
|  | External Tasks | Duration-only |  | Progress
Page 15

## Sheet17
Resource Names | 2, '16 | Oct 9, '16 | Oct 16, '16 | Oct 23, '16 | Oct 30, '16
M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S
Shunmugam
Guru
Prabakar
Selva
Prabakar
Prabakar
Prabakar
Prabakar
Elan
Selva
Shunmugam
Shunmugam
Shunmugam
Shunmugam
Shunmugam
Shunmugam
Shunmugam
Elan
Reshmi
Guru
Guru
|  | Task | External Milestone |  | Manual Summary Rollup
|  | Split | Inactive Task |  | Manual Summary
Project: Sling_ProjectPlan_V1.0.m |  | Milestone | Inactive Milestone |  | Start-only
Date: Sat 10/15/16 |  | Summary | Inactive Summary |  | Finish-only
|  | Project Summary | Manual Task |  | Deadline
|  | External Tasks | Duration-only |  | Progress
Page 16

## Sheet18
Resource Names | 2, '16 | Oct 9, '16 | Oct 16, '16 | Oct 23, '16 | Oct 30, '16
M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S
Guru
Guru
Vinoth
Vinoth
Elan
Guru
Reshmi
Vinoth
Prabakar
Prabakar
Reshmi
Prabakar
Prabakar
Selva
Guru
Guru
Guru
Guru
Baskar
QA Team
|  | Task | External Milestone |  | Manual Summary Rollup
|  | Split | Inactive Task |  | Manual Summary
Project: Sling_ProjectPlan_V1.0.m |  | Milestone | Inactive Milestone |  | Start-only
Date: Sat 10/15/16 |  | Summary | Inactive Summary |  | Finish-only
|  | Project Summary | Manual Task |  | Deadline
|  | External Tasks | Duration-only |  | Progress
Page 17

## Sheet19
Resource Names | 2, '16 | Oct 9, '16 | Oct 16, '16 | Oct 23, '16 | Oct 30, '16
M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S
Client
Prabakar
Client
Reddy |  |  |  | Reddy
Reddy |  |  |  |  | Reddy
Reddy |  |  |  |  | R
Elan
Elan
Elan
Elan
Selva
Elan
Selva
Elan
Selva
Elan
Elan
Elan
Reshmi
|  | Task | External Milestone |  | Manual Summary Rollup
|  | Split | Inactive Task |  | Manual Summary
Project: Sling_ProjectPlan_V1.0.m |  | Milestone | Inactive Milestone |  | Start-only
Date: Sat 10/15/16 |  | Summary | Inactive Summary |  | Finish-only
|  | Project Summary | Manual Task |  | Deadline
|  | External Tasks | Duration-only |  | Progress
Page 18

## Sheet20
Resource Names | 2, '16 | Oct 9, '16 | Oct 16, '16 | Oct 23, '16 | Oct 30, '16
M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S
Prabakar
Reshmi
Elan
Elan
Reshmi
Prabakar
Prabakar
Prabakar
Prabakar
Reshmi
Elan
Elan
Elan
Reshmi
Elan
Elan
Elan
Reshmi
Indu
Praveen
|  | Task | External Milestone |  | Manual Summary Rollup
|  | Split | Inactive Task |  | Manual Summary
Project: Sling_ProjectPlan_V1.0.m |  | Milestone | Inactive Milestone |  | Start-only
Date: Sat 10/15/16 |  | Summary | Inactive Summary |  | Finish-only
|  | Project Summary | Manual Task |  | Deadline
|  | External Tasks | Duration-only |  | Progress
Page 19

## Sheet21
Resource Names | 2, '16 | Oct 9, '16 | Oct 16, '16 | Oct 23, '16 | Oct 30, '16
M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S
Indu
Praveen
Indu
Praveen
Indu
Praveen
Indu
Prabakar
Prabakar
Client
Jeena
Prabakar
Baskar
Baskar
Vinoth
Shunmugam
Prabakar
Jeena
Nat
|  | Task | External Milestone |  | Manual Summary Rollup
|  | Split | Inactive Task |  | Manual Summary
Project: Sling_ProjectPlan_V1.0.m |  | Milestone | Inactive Milestone |  | Start-only
Date: Sat 10/15/16 |  | Summary | Inactive Summary |  | Finish-only
|  | Project Summary | Manual Task |  | Deadline
|  | External Tasks | Duration-only |  | Progress
Page 20

## Sheet22
| Nov 6, '16 | [6 empty] | Nov 13, '16 | [6 empty] | Nov 20, '16 | [6 empty] | Nov 27, '16 | [7 empty] | Dec 4, '16 | [6 empty] | Dec 11, '1
S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
Reddy

## Sheet23
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 21

## Sheet24
| Nov 6, '16 | [7 empty] | Nov 13, '16 | [6 empty] | Nov 20, '16 | [6 empty] | Nov 27, '16 | [6 empty] | Dec 4, '16 | [6 empty] | Dec 11, '1
S |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M

## Sheet25
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 22

## Sheet26
| Nov 6, '16 | [7 empty] | Nov 13, '16 | [6 empty] | Nov 20, '16 | [6 empty] | Nov 27, '16 | [6 empty] | Dec 4, '16 | [6 empty] | Dec 11, '1
S |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
Elan

## Sheet27
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 23

## Sheet28
Nov 6, '16 | Nov 13, '16 | Nov 20, '16 | Nov 27, '16 | Dec 4, '16 | Dec 11, '1
S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M
Prabakar
Selva
Elan
Selva
Guru
Guru
Shunmugam
Shunmugam
Shunmugam
Baskar
QA Team
Client

## Sheet29
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 24

## Sheet30
| Nov 6, '16 | [7 empty] | Nov 13, '16 | [6 empty] | Nov 20, '16 | [6 empty] | Nov 27, '16 | [6 empty] | Dec 4, '16 | [6 empty] | Dec 11, '1
S |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M

## Sheet31
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 25

## Sheet32
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 26

## Sheet33
Nov 6, '16 | Nov 13, '16 | Nov 20, '16 | Nov 27, '16 | Dec 4, '16 | Dec 11, '1
S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M
Guru
Guru
Vinoth
Vinoth
Guru
Reshmi

## Sheet34
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 27

## Sheet35
| Nov 6, '16 | [7 empty] | Nov 13, '16 | [6 empty] | Nov 20, '16 | [6 empty] | Nov 27, '16 | [6 empty] | Dec 4, '16 | [6 empty] | Dec 11, '1
S |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M

## Sheet36
Reshmi
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 28

## Sheet37
| Nov 6, '16 | [7 empty] | Nov 13, '16 | [6 empty] | Nov 20, '16 | [6 empty] | Nov 27, '16 | [6 empty] | Dec 4, '16 | [6 empty] | Dec 11, '1
S |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
Reshmi

## Sheet38
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 29

## Sheet39
| Nov 6, '16 | [6 empty] | Nov 13, '16 | [6 empty] | Nov 20, '16 | [7 empty] | Nov 27, '16 | [6 empty] | Dec 4, '16 | [6 empty] | Dec 11, '
S | S | M | T | W | T | F | S | S | M | T | W | T | F | S |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M

## Sheet40
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 30

## Sheet41
16 |  |  |  |  | Dec 18, '16 | [6 empty] | Dec 25, '16 | [6 empty] | Jan 1, '17 | [6 empty] | Jan 8, '17 | [6 empty] | Jan 15, '17
T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T

## Sheet42
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 31

## Sheet43
16 |  |  |  |  | Dec 18, '16 | [6 empty] | Dec 25, '16 | [6 empty] | Jan 1, '17 | [6 empty] | Jan 8, '17 | [6 empty] | Jan 15, '17
T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T

## Sheet44
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 32

## Sheet45
16 |  |  |  |  | Dec 18, '16 | [6 empty] | Dec 25, '16 | [6 empty] | Jan 1, '17 | [6 empty] | Jan 8, '17 | [6 empty] | Jan 15, '17
T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T

## Sheet46
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 33

## Sheet47
16 |  |  |  |  | Dec 18, '16 | [6 empty] | Dec 25, '16 | [7 empty] | Jan 1, '17 | [7 empty] | Jan 8, '17 | [6 empty] | Jan 15, '17
T | W | T | F | S | S | M | T | W | T | F | S |  | S | M | T | W | T | F | S |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T

## Sheet48
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 34

## Sheet49
16 |  |  |  |  | Dec 18, '16 | [6 empty] | Dec 25, '16 | [7 empty] | Jan 1, '17 | [7 empty] | Jan 8, '17 | [6 empty] | Jan 15, '17
T | W | T | F | S | S | M | T | W | T | F | S |  | S | M | T | W | T | F | S |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T

## Sheet50
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 35

## Sheet51
16 |  |  |  |  | Dec 18, '16 | [6 empty] | Dec 25, '16 | [6 empty] | Jan 1, '17 | [6 empty] | Jan 8, '17 | [6 empty] | Jan 15, '17
T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T

## Sheet52
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 36

## Sheet53
16 |  |  |  |  | Dec 18, '16 | [6 empty] | Dec 25, '16 | [7 empty] | Jan 1, '17 | [7 empty] | Jan 8, '17 | [6 empty] | Jan 15, '17
T | W | T | F | S | S | M | T | W | T | F | S |  | S | M | T | W | T | F | S |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T

## Sheet54
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 37

## Sheet55
16 | Dec 18, '16 | Dec 25, '16 | Jan 1, '17 | Jan 8, '17 | Jan 15, '17
T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T
Client
Prabakar
Client
Elan
Elan
Elan
Elan
Elan
Elan
Elan
Elan
Elan
|  | Task | External Milestone | Manual Summary Rollup
|  | Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m |  | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 |  | Summary | Inactive Summary | Finish-only
|  | Project Summary | Manual Task | Deadline
|  | External Tasks | Duration-only | Progress
Page 38

## Sheet56
16 |  |  |  |  | Dec 18, '16 | [6 empty] | Dec 25, '16 | [7 empty] | Jan 1, '17 | [6 empty] | Jan 8, '17 | [7 empty] | Jan 15, '17
T | W | T | F | S | S | M | T | W | T | F | S |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F |  | S | S | M | T | W | T
Prabakar
Elan
Elan
Pra

## Sheet57
Indu
Praveen
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 39

## Sheet58
16 |  |  |  |  | Dec 18, '16 | [6 empty] | Dec 25, '16 | [7 empty] | Jan 1, '17 | [7 empty] | Jan 8, '17 | [6 empty] | Jan 15, '17
T | W | T | F | S | S | M | T | W | T | F | S |  | S | M | T | W | T | F | S |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
Indu
Praveen

## Sheet59
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 40

## Sheet60
|  | Jan 22, '17 | [7 empty] | Jan 29, '17 | [6 empty] | Feb 5, '17 | [6 empty] | Feb 12, |  | '17 | [5 empty] | Feb 19, |  | '17 | [5 empty] | Feb
F | S | S | M | T | W | T | F | S | S |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M |  | T | W | T | F | S | S | M |  | T | W | T | F | S | S

## Sheet61
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 41

## Sheet62
|  | Jan 22, '17 | [7 empty] | Jan 29, '17 | [6 empty] | Feb 5, '17 | [6 empty] | Feb 12, |  | '17 | [5 empty] | Feb 19, |  | '17 | [5 empty] | Feb
F | S | S | M | T | W | T | F | S | S |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M |  | T | W | T | F | S | S | M |  | T | W | T | F | S | S

## Sheet63
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 42

## Sheet64
|  | Jan 22, '17 | [7 empty] | Jan 29, '17 | [6 empty] | Feb 5, '17 | [6 empty] | Feb 12, |  | '17 | [5 empty] | Feb 19, |  | '17 | [5 empty] | Feb
F | S | S | M | T | W | T | F | S | S |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M |  | T | W | T | F | S | S | M |  | T | W | T | F | S | S

## Sheet65
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 43

## Sheet66
|  | Jan 22, '17 | [7 empty] | Jan 29, '17 | [6 empty] | Feb 5, '17 | [6 empty] | Feb 12, |  | '17 | [5 empty] | Feb 19, |  | '17 | [5 empty] | Feb
F | S | S | M | T | W | T | F | S | S |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M |  | T | W | T | F | S | S | M |  | T | W | T | F | S | S

## Sheet67
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 44

## Sheet68
|  | Jan 22, '17 | [7 empty] | Jan 29, '17 | [6 empty] | Feb 5, '17 | [6 empty] | Feb 12, |  | '17 | [5 empty] | Feb 19, |  | '17 | [5 empty] | Feb
F | S | S | M | T | W | T | F | S | S |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M |  | T | W | T | F | S | S | M |  | T | W | T | F | S | S

## Sheet69
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 45

## Sheet70
|  | Jan 22, '17 | [7 empty] | Jan 29, '17 | [6 empty] | Feb 5, '17 | [6 empty] | Feb 12, |  | '17 | [5 empty] | Feb 19, |  | '17 | [5 empty] | Feb
F | S | S | M | T | W | T | F | S | S |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M |  | T | W | T | F | S | S | M |  | T | W | T | F | S | S

## Sheet71
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 46

## Sheet72
|  | Jan 22, '17 | [7 empty] | Jan 29, '17 | [6 empty] | Feb 5, '17 | [6 empty] | Feb 12, |  | '17 | [5 empty] | Feb 19, |  | '17 | [5 empty] | Feb
F | S | S | M | T | W | T | F | S | S |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M |  | T | W | T | F | S | S | M |  | T | W | T | F | S | S

## Sheet73
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 47

## Sheet74
|  | Jan 22, '17 | [7 empty] | Jan 29, '17 | [6 empty] | Feb 5, '17 | [6 empty] | Feb 12, |  | '17 | [5 empty] | Feb 19, |  | '17 | [5 empty] | Feb
F | S | S | M | T | W | T | F | S | S |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M |  | T | W | T | F | S | S | M |  | T | W | T | F | S | S

## Sheet75
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 48

## Sheet76
|  | Jan 22, '17 | [6 empty] | Jan 29, '17 | [6 empty] | Feb 5, '17 | [6 empty] | Feb 12, |  | '17 | [5 empty] | Feb 19, |  | '17 | [6 empty] | Feb
F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M |  | T | W | T | F | S | S | M |  | T | W | T | F | S | S

## Sheet77
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 49

## Sheet78
|  | Jan 22, '17 | [6 empty] | Jan 29, '17 | [6 empty] | Feb 5, '17 | [6 empty] | Feb 12, |  | '17 | [5 empty] | Feb 19, |  | '17 | [6 empty] | Feb
F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M |  | T | W | T | F | S | S | M |  | T | W | T | F | S | S

## Sheet79
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 50

## Sheet80
26, | '17 | [5 empty] | Mar 5, '17 | [6 empty] | Mar 12, '17 | [6 empty] | Mar 19, '17 | [6 empty] | Mar 26, '17 | [6 empty] | Apr 2, '17
M |  | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S |  | S | M | T | W

## Sheet81
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 51

## Sheet82
26, | '17 | [5 empty] | Mar 5, '17 | [6 empty] | Mar 12, '17 | [6 empty] | Mar 19, '17 | [6 empty] | Mar 26, '17 | [6 empty] | Apr 2, '17
M |  | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S |  | S | M | T | W

## Sheet83
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 52

## Sheet84
26, | '17 | [5 empty] | Mar 5, '17 | [6 empty] | Mar 12, '17 | [6 empty] | Mar 19, '17 | [6 empty] | Mar 26, '17 | [6 empty] | Apr 2, '17
M |  | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S |  | S | M | T | W

## Sheet85
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 53

## Sheet86
26, | '17 | [5 empty] | Mar 5, '17 | [6 empty] | Mar 12, '17 | [6 empty] | Mar 19, '17 | [6 empty] | Mar 26, '17 | [6 empty] | Apr 2, '17
M |  | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S |  | S | M | T | W

## Sheet87
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 54

## Sheet88
26, | '17 | [5 empty] | Mar 5, '17 | [6 empty] | Mar 12, '17 | [6 empty] | Mar 19, '17 | [6 empty] | Mar 26, '17 | [6 empty] | Apr 2, '17
M |  | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S |  | S | M | T | W

## Sheet89
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 55

## Sheet90
26, | '17 | [5 empty] | Mar 5, '17 | [6 empty] | Mar 12, '17 | [6 empty] | Mar 19, '17 | [6 empty] | Mar 26, '17 | [6 empty] | Apr 2, '17
M |  | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S |  | S | M | T | W

## Sheet91
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 56

## Sheet92
26, | '17 | [5 empty] | Mar 5, '17 | [6 empty] | Mar 12, '17 | [6 empty] | Mar 19, '17 | [6 empty] | Mar 26, '17 | [6 empty] | Apr 2, '17
M |  | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S |  | S | M | T | W

## Sheet93
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 57

## Sheet94
26, | '17 | [5 empty] | Mar 5, '17 | [6 empty] | Mar 12, '17 | [6 empty] | Mar 19, '17 | [6 empty] | Mar 26, '17 | [6 empty] | Apr 2, '17
M |  | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S |  | S | M | T | W

## Sheet95
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 58

## Sheet96
26, | '17 | [5 empty] | Mar 5, '17 | [6 empty] | Mar 12, '17 | [6 empty] | Mar 19, '17 | [6 empty] | Mar 26, '17 | [6 empty] | Apr 2, '17
M |  | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S |  | S | M | T | W

## Sheet97
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 59

## Sheet98
26, | '17 | [5 empty] | Mar 5, '17 | [6 empty] | Mar 12, '17 | [6 empty] | Mar 19, '17 | [6 empty] | Mar 26, '17 | [6 empty] | Apr 2, '17
M |  | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W

## Sheet99
| Task | External Milestone | Manual Summary Rollup
| Split | Inactive Task | Manual Summary
Project: Sling_ProjectPlan_V1.0.m | Milestone | Inactive Milestone | Start-only
Date: Sat 10/15/16 | Summary | Inactive Summary | Finish-only
| Project Summary | Manual Task | Deadline
| External Tasks | Duration-only | Progress
Page 60